## Sheet1
BEN Community
Work | 2017.04 (April) |  |  |  | 2017.05(May) |  |  |  |  | 2017.06(June)
| 1 Week | 2 Week | 3 Week | 4 Week | 1 Week | 2 Week | 3 Week | 4 Week | 5 Week | 1 Week
Program Dev |  | * Create Project Name : BEN_Community (100%) * Creare Database Name: BENCommunity (100%) * Download and refer source files (100%) * Use the Telerik MVC & Kendo Last version / .NET Framework 4.x UP / MVC 5.0 (100%) * Member Login Page (70%)(I am reading Naver Login API) | * BEN Login page (90%) * BEN Register page (90%) * BEN Home page (20%) | * BEN Login page (100%) * BEN Register page (100%) * BEN Home page (20%) | * BEN Home page (100%) * Ben Member page (100%) |  | * Mofidy master page layout (100%) * Move Login Page (100%) *Fix wrong Korea text (100%) * Add the Common Code in Register page (100%) Mofidy Edit Account page (50%) | Next task: Mofidy Edit Account page (100%) Project page (20%) | Project page 80% System page 10% | Next task: System page. Test and Fix bugs.
Test & Modify
Realese |  | First source project